Preliminary report of ICF13 Status:

To: ICF Executive Committee of ICF;17th,June,2013,Beijing,CHINA

By: Shouwen Yu, Executive Chairman-- ICF13.

Organizer:

The 13th International Conference on Fracture (ICF13) is to be held on June 16–21, 2013. The conference is organized by The Chinese Society of Theoretical and Applied Mechanics, Fracture Group of Hong Kong of China, Chinese Mechanical Engineering Society, Chinese Materials Research Society, Chinese Society of Corrosion and Protection, Chinese Society of Aeronautics and Astronautics, The China Structural Integrity Consortium, and Chinese Society for Metals. Professor Shouwen Yu of Tsinghua University works as the chairman, and Professor Wei Yang (President of National Natural Science Foundation of China) and Professor Tongyi Zhang of Hong Kong University of Science and Technology serve as the co-chairmen. Conference secretaries are Professor Xi-Qiao Feng of Tsinghua University and Professor Yazheng Yang of Chinese Society of Theoretical and Applied Mechanics. The organizing committee has worked for four years to create a successful conference.

Board and Technical plan;

ICF13 has invited an International Scientific Advisory Board consisting of 54 world-famous scholars. 196 influential scientists and engineers working on the frontline of the fields of fracture and the relevant compose the International Scientific Committee and are in charge of the organization and technical standard of the 54 Sessions and 15 Mini-Symposiums on ICF13. These Sessions and Mini-Symposiums are dedicated to the development and innovation in not only the traditional and fundamental topics but also the exciting and edge-cutting arenas—from biomedicine to geophysics, from nano/atomic to macro scales, and from physical to holistic and system modeling.

Honor Lectures and Plenary Lectures:

In addition to the parallel sessions, ICF13 provides 3 Honor Lectures and 13 Plenary Lectures. The Opening Honor Lecture will be given by Professor Subra Suresh (USA); the Presidential Honour Lecture will be given by Professor Alberto Carpinteri (Italy); the Closing Honor Lecture will be given by Professor Yiu-Wing Mai (Australia). 13 Plenary Lectures will be delivered by Professor James R. Rice (USA), Professor J.W. Hutchinson (USA), Professor Huajian Gao(USA), Professor B. L. Karihaloo (UK), Professor Wei Yang (China), Professor Yuri V. Petrov (Russia), Professor Qingping Sun (Hong Kong, China), Professor Reinhard Pippan (Austria), Professor Peter Gumbsch (Germany), Professor Y. Murakami (Japan), Professor Ashok Saxena (USA), Professor Jun Sun (China), and Professor Wing Kam Liu (USA). Very recently, Professor Wing Kam Liu has cancelled his plenary lecture due to his personal reason.

Abstracts/paper submission and registration:

The abstract submissions of ICF13 began on May, 2012. All submissions were managed through the internet. In six months, ICF13 received 1256 submissions. After peer review, 1154 submissions were finally accepted to be included in the conference program and be orally presented on the conference. 636 full papers will be including in the ICF13 Proceedings in CD-Rom form. The acceptance letters of abstract and full papers were sent on November, 2012 and March, 2013, respectively. The online registration started on February, 2013.910 delegates from 46 counties all over the world  have registered by 6th,June, 2013. The technical program of the conference was published on May 20, 2013. The organizing committee of ICF13 has been prepared to welcome the participants all over the world. It is expected that 900 – 1000 scientists ,engineers and graduate students from about fifty countries will attend the coming ICF13.

Conference Venue

The Conference Venue is the China National Convention Center (CNCC) which is ideally located in the heart of the Olympic Green of Beijing, adjacent to the National Stadium (Bird’s Nest) and the National Aquatics Center (Water Cube).

Abstract /Paper Press

All accepted papers are published in the proceedings of ICF13 in the form of CD-ROM. The proceedings, together with a book of Abstracts, are provided to the participants at registration. Selected papers will be published, after peer review, in some special issues of international journals.

ICF13 Web and Registration System

ICF13 Web established in the end of 2010 with completed Academic Conference-System. 910 delegates from 46 counties all over the world registered in the system. Each one could get a Registration Number to help them do to find the information rapidly. And we also accept the delegate registration on site.

Invitation Letter for Visa

When hosting an international meeting, most delegates come from abroad, and many of them require an entry visa. Upon receiving the registration information from the delegates, the Conference Secretariat  sent them the official invitation letters issued by the China Association for Science and technology ( CAST ). The Conference Secretariat fax or mail the Visa Invitation Form to  registered delegates to help them initiate their application.

Volunteers

The ICF13 Organizing Committee would like to make attendees aware of the group of university students who have volunteered their time to assist in making your experience at the conference an enjoyable one. Delagates could see them at the Registration Desk, in the Information Center, the Internet Center, the Speaker Ready Room and in the session rooms. To facilitate recognition, they are all in the green T-shirts with ICF13 conference logo on the front.

Speaker Ready Room /Internet Center

All presenters upload their presentation to an M Events protected sever prior to arrival or onsite at the Speaker Ready Room prior to their scheduled presentations. The presentations are delivered to the lecture rooms via a network-based presentation system, which ensure perfect quality of all presentations along with a conference-specific interface. All meeting rooms are equipped with the necessary technical requirements, and additional back-up systems.

WIFI access the Internet are provided in the CNCC. Meanwhile, a computer area has been reserved and set up for all registered conference delegates to access the Internet in order to send and retrieve e-mails, which is located in the main lobby of CNCC.

Exhibition

About 10 Booksellers, scientific instrument manufacturers and software vendors and other firms interested in presenting their products and services are invited to sponsor vendor exhibits at ICF13.

Medical Service at Conference Office

The medical service is provided for the participants during the conference in the Conference Office room. Participants also could go to the Conference Office for help in case of the Registration Desk unavailable.

Food

We provide the reception and lunches with delicious Chinese food during the conference for all the regular participates as well as students participates for free. And there is also a banquet available for the delegates.

Accommodation

There are a number of hotels of different categories, close to the Conference Venue. We recommend 4 hotels in the registration system with special rates for Conference attendees. ICF13 participants could use the Registration System to do the hotel reservation. And we also provide the information of 11 different hotels on the website for the delegates.

Art player

ICF13 invite the Chinese Traditional philharmonic to play the folk music to the delegates on the Opening Ceremony.

Tour & Travel

Beijing is a famous oriental city with profound history and splendid culture. A company is hired to provide information for many tours that are available during the peak tourist season in Beijing. The delegates could book the city tours, post conference tours as well as the airport pick-up from the registration system.

Fundraising and sponsorship:

Fundraising group have established for linking organizations, foundations, associations and universities for the sponsorship of ICF13.

Appendix: Time Table

| 2010 | Web Site Development |
| --- | --- |
| June 30, 2011 | First Announcement |
| Mar. 31, 2012 | Second Announcement and Call for Papers |
| Oct. 31, 2012 | Deadline for Submission of Abstracts |
| Nov. 25, 2012 | Notification of Acceptance of Abstracts |
| Feb. 28, 2013 | Deadline for Submission of Papers |
| Mar. 25, 2013 | Notification of Acceptance of Papers |
| Mar. 31, 2013 | Deadline for Early Bird Registration |
| May 14, 2013 | Deadline for Hotel Reservation and Cancellation |
| June 16 - 21 | Conference (ICF13) |